## Slide 1: Monitoring and Evaluation Key Concepts
Overview of M&E Capacity Building Initiative

## Slide 2: M&E Capacity Building Cycle
Ongoing: One-on-one discussions
Round 1
Round 2
People with M&E Responsibility
Conceptual M&E Plan
Responsibilities
Concepts
Roles
Round 3
People with M&E Responsibility
Specific M&E Topics
Management and M&E Staff
Increased M&E Capacity
NAG Myanmar
Cuso International

## Slide 3: Monitoring and Evaluation Key Concepts
What is M&E?
What is a Project ?
What is an Indicator?
Why M&E?
M&E Organizational Issues
Ideal vs. Reality

## Slide 4: What is M&E?
Monitoring
regularly collecting, reviewing, reporting and acting on information about project implementation
Monitoring addresses: What Is?
Evaluation
an periodic in-depth, backward - looking analysis of (parts of) a project
Evaluation addresses: Why?
M&E = Management Information
Indicators are the currency of M&E
  They determine which data to gather
  Analysis of indicator data underpins information to Management
Monitoring What is?
Evaluation Why?
Overlap: analyzing and interpreting monitoring data

## Slide 5: From Monitoring to Evaluation
Monitoring
  Good indicators
  Rigorous data
Small “e” Evaluation
  Data interpretation
  From Data to Information
Formal Evaluation
  Mid term
  Final
Focus on Monitoring and Small “e” Evaluation
Overlap: small “e” evaluation analyzing and interpreting monitoring data
Monitoring: What is
Evaluation: Why?

## Slide 6: Monitoring and Evaluation Key Concepts
Project
What we actually doing
Model of the Project
Logical Framework (inputs, outputs, outcomes)
Selected Points of Measurement
Indicators
M&E

## Slide 7: Logical Framework (Log Frame)
Goal
Outputs
Inputs
Outcomes
Activities
Shows the logic/theory of change of the Project
Planning tool
  What to achieve
  How to do it.
Broadly accepted tool
  General consensus re. wording
  Objectives = Outcomes
  Goals = Ultimate Outcomes
Objectives

## Slide 8: Logical Framework (Log Frame)
Goal
Outputs
Inputs
Outcomes
Activities
Goal: lofty statement
  May or may not be measurable
Outcomes translate the goal into measureable and manageable pieces
Outcomes bring te lofty goal down to earth. They are:
  Specific
  Measurable
  Achievable
  Relevant
  Time-bound
Outcomes are the end-state we want to achieve

## Slide 9: Logical Framework (Log Frame)
Goal
Outputs
Inputs
Outcomes
Activities
Project controls Inputs, Activities, and Outputs
Others (Recipients) need to act if objectives are to be reached
  Project assumes that Outputs will contribute to desired end stages (i.e. objectives)
  Assumption needs to be tested
Notes: Lots of examples of inputs/activities/outputs:
NAG: Inputs (community mobilizers, motor bikes) Activity (community level meetings, training sessions). Output: working community groups
BUT COMMUNITY GROUPS NEED TO ACT TO HAVE INFLUENCE ON FISHERIES GOVERANCE OR LIVELIHOODS
EM: Inputs (trainers, curriculum, travel budgets) Activity (human rights training) Output: CSO groups with increased Human Rights awareness
BUT CSO NEED TO ACT TO IMPROVE HUMAN RIGHTS SITUATION IN MYANMARE
CESD: Inputs (researches, travel budgets); Activity (data gathering, analysis, report writing); Output: Research report
BUT GOVERNMENTS AND OTHER STAKEHOLDERS HAVE TO ACT TO REALIZE REPORTS’ IMPACT ON POLICY

## Slide 10: Monitoring and Evaluation Key Concepts
What are Indicators?

## Slide 11: What is an Indicator?
Webster Dictionary
  A sign that shows the condition or existence of something
  A pointer or light that shows the state or condition of something
  A device that shows a measurement
Some Examples
  Fever as an indicator for sickness
  3G light on cell phone as indicators for connectivity
Indicators are a reflection of the underlying item

## Slide 12: Indicators
Indicator(s) for Goal
Descriptors of Inputs
Indicator(s) for Outcomes
Descriptors of Outputs
Descriptors of Activities
Outcomes are the end-state we want to achieve.
If we achieve Project Outcomes, the Project Logic indicates that we have moved towards the overall Goal
Outcome = Indicators for Goal
Notes: Goal: Vulnerable people in GoM have improved livelihood security
Objectives: Fisheries Co-management; Fishers have more power in value chain; Livelihood alternatives;
In other words: If we reach the objectives, than we feel we have made a substantial contribution to the goal.
Other objectives are possible. E.g. vocational training;

## Slide 13: Indicators/Descriptors
Indicator(s) for Goal
Descriptors of Inputs
Indicator(s) for Outcomes
Descriptors of Outputs
Descriptors of Activities
Inputs, activities, and outputs are concrete
  Can be described fully
  No need for proxies
Indicator = Description for inputs, activities, and outputs

## Slide 14: Indicators
Indicator(s) for Goal
Descriptors of Inputs
Indicator(s) for Outcomes
Descriptors of Outputs
Descriptors of Activities
Need indicators for Outcomes
  Even SMART Objectives are multi-faceted
  Indicators are proxies for desired end states (i.e. objectives)
Indicator makes Outcomes concrete or real
SMART Outcomes have SMart indicators
  Specific
  Measurable
Notes: Goal: Vulnerable people in GoM have improved livelihood security
Objectives: Fisheries Co-management; Fishers have more power in value chain; Livelihood alternatives;
In other words: If we reach the objectives, than we feel we have made a substantial contribution to the goal.
Other objectives are possible. E.g. vocational training;

## Slide 15: Key Concepts Summary
M&E is management information for a Project
M&E is based on a Project’s Logical Framework
Indicators are used to capture all elements of the Logical Framework
  Goal
  Outcomes
  Outputs
  Inputs, Activities, Outputs
Key take-away:
Tight formulation of Outcomes: Make outcomes specific
Few but “telling” outcome indicators
Model of the Project
Logical Framework (inputs, outputs, outcomes)
Selected Points of Measurement
Indicators
M&E

## Slide 16: Monitoring and Evaluation Key Concepts
Why M&E?
Project and Organization M&E?

## Slide 17: Why M&E ?
M&E provides basis for Corrective Action
Inputs
Activities
Outputs
Outcomes/ Objectives
Goal
Need for Management Information
Inputs
Activities
Outcomes/ Objectives
Goal
Outputs
Objectives not Reached
M&E Based Corrective Action
Side Benefits of M&E
Easier Donor Reporting

## Slide 18: Organization M&E
Focus on Your Organization
Your Organization has a concept of itself
  Strategic Plan
  Organization Log Frame
Organization has Corporate M&E: management information, including financial information
  Budget
  Tracking of Expenditures
  Analysis of Variance
Organization’s Log Frame captures its “Essence”
Projects are “means to an end”
Organization Goal
Outputs (incl. Projects)
Inputs (incl. Projects)
Outcomes
Activities (incl. Projects)

## Slide 19: Organizational and Project Log Frames
Matching Project
Project aligns with Organization Log Frame
Organization grows/learns from Project in line with its Strategic Direction
Non Matching Project
Project does not align with Log Frame
Organization learns from Project but changes in the process
May lead to lack of focus
May need to rethink Organization’s strategic plan
Organization
Project
Organization
Project

## Slide 20: Organizational and Project M&E
Matching Projects
Project aligns with Organization M&E
Project M&E substantially satisfied Organizational M&E requirements
Organization grows/learns from Project in line with its Strategic Direction
Organization M&E
Project
M&E
Organization M&E
Project M&E
Non Matching Projecta
Project does not align with Organization M&E
Project M&E does not satisfied Organizational M&E requirements
Organization learns from Project but changes in the process

## Slide 21: Summary: Projects and Organization
Organizations define themselves in a Strategic Plan or Organizational Log Frame
Organizations show themselves through Projects
Organizational learning/ growth occurs when Projects align with Organization’s goals
Project management information (M&E) becomes management information for the Organization

## Slide 22: Monitoring and Evaluation Key Concepts
Organizational Issues

## Slide 23: Project M&E Flowchart
Execution plan
Sector Manager
M&E Implementation
Manager/Staff
Proposal/T of R
Management
Implementation
Sector Manager
M&E Plan
Sector Manager
Lessons Learned
Manager/Staff
Objectives Reached
Sector Manager

## Slide 24: Roles and Responsibility
M&E Plan
Indicators of
Objectives
Inputs/Activities/Outputs
M&E Implementation
Baseline/monitoring data gathering
Data Analysis
Report Writing
Program Manager is responsible for M&E Plan
Staff involvement depends capability
Program staff do the bulk of the work
Supervised by Program Manager
Sector Manager
Staff
Sector Manager
Staff

## Slide 25: Monitoring and Evaluation Key Concepts
Ideal vs. Reality

## Slide 26: Ideal versus Reality
Ideal
M&E is Management Information System
M&E Plan completed at Project outset
M&E pervades all Project elements
Completed Projects Inform new Projects
Reality
M&E is seen as burdensome donor requirement
No formal M&E Plan
M&E is afterthought
Informal lessons learned only
Ideal sets the direction for M&E Improvement process

## Slide 27: NEXT STEPS
Process towards M&E
M&E work plan (Feb?)
  Situation Analysis
    Alignment of organizational and key project log frames
    Indicators used/needed
  Development Plan (March?)
    Indicators/sources
    Data analysis
    Roles and responsibilities
  Implementation (April – Sept)
Medium-term Priority
New Executive Director in place in near term
M&E Plan is opportunity to reflect on the organization
    What is its focus?
    Who does it serve?
    What Management Information does it need
No direct demand from donor as MBE is mostly self-funded